## Meet links
TIME | MEETING LINK | Days | next date | MOM
10:00AM-11:00AM | https://meet.google.com/kej-vzxv-ucc | Monday and Wednes day
3:00 PM to 4:00PM | https://meet.google.com/gow-cbrv-csx | Friday | 2022-06-15 | Discuss about PREPORD DB upgrade
3:00PM to 4:00PM | https://teams.microsoft.com/l/meetup-join/19%3ameeting_NWIzYzI0ZjMtMjZlOC00YzViLTk4OGItMDJmNTA3ZThmNjUy%40thread.v2/0?context=%7b%22Tid%22%3a%22404b1967-6507-45ab-8a6d-7374a3f478be%22%2c%22Oid%22%3a%2230ff84c2-58d3-40b8-a252-0e163d6fff17%22%7d | Monday and Friday | 14-06022 | 1.Discussed about the sheet prepared by team 2.Today we need to provide the timeline and the solution for 3 issues a.Provision related issues b.Change Entity issues c.CMTS issues
5:00PM to 6:00 PM | https://teams.microsoft.com/l/meetup-join/19%3ameeting_NWIzYzI0ZjMtMjZlOC00YzViLTk4OGItMDJmNTA3ZThmNjUy%40thread.v2/0?context=%7b%22Tid%22%3a%22404b1967-6507-45ab-8a6d-7374a3f478be%22%2c%22Oid%22%3a%2230ff84c2-58d3-40b8-a252-0e163d6fff17%22%7d | Monday | 2022-06-20 | MOM of Hathway Discussion: CMTS issue Rama sir informed to raise AD BCC gets : Ned to change role from static to Dynamic how BCC request got deleted Get a provision order from NOc team and Pandu will provide it then BRM team need to investigate Missing entitlement error: ISP not getting this type Client class ID: CMTS is deactivated in Sterilite Subscriber ID missing: Whenever User deleted GPON saying subscriber id is missing Debjani has to follow up with Rohan to further investigation Provisiong failed alternate id does not exist: Users are deleting mac through OAP As per Rohan, Hemangi is going to send mail to disable delete tab from OAP Plan is showing inactive Order was not executed on FFriday so it Rama sir and Umar are working Invalid argument request: Need the analysis for failure for this error from ASAP Sending wrong plan and package in sterelite Task Id is not matching with BRM : ASAP team need to investigate Provisiong tag creation/user id creation/Bouquet id creation: Rama sir Reuested these functionalities are availbale in OAP
17:30 | https://meet.google.com/dkp-dhtv-yox | Monday | 2022-06-20 | FTA block in selective region: This change is applicable for DEN now. - existing set bouquet id command will go for a change - Impacted workflow should be validated & confirmed by Debjani (activation, single bouquet, reactivation, retrack, authorize, change bouquet id, cancel, etc workflows may have an impact). - Debjani to provide the modified command to be sent. - Rohan to confirm the command sent by Debjani. - BRM & ASAP to modify the existing command on all the impacted workflows. BRM to develop an API to trigger the command from backend. OAP should be able to send the command to network element. Following is the priority to be considered for the deployment of BRM & ASAP changes. Command 21, Command 77 & VU id changes are already offered to UAT FTA block enablement JVM reset pin changes Broadcast mode changes"
| https://meet.google.com/rsi-hkhh-qvi?authuser=0 | DBA Some of the BRM application generated sql statements where leading to high memory consumption and causing BRM system going into hung state. Idenfitied query was re-written in better manner by BRM team. Post fix there is no reoccurancce of issue. Similarly there may be multiple SQL queries which will be checked by BRM team.
Optimization call | https://meet.google.com/gow-cbrv-csx
CIO Dashboard | https://meet.google.com/rsi-hkhh-qvi?authuser=0

## Optimization call
Date | Discussion | Meet link: | https://meet.google.com/gow-cbrv-csx
2022-07-18 | Discussed on DB and later they worked DB issue
2022-07-21 | Purging of product is going on and finish by tomorrow Rama sir need to share temp tables Regarding reclaining Suggested for all actions for one partition and Atee is working on the same To avoid multiple compressions need to purge only 10million records Raw CDR purging needs to be initiated by Vineet Stop rating and again need to run the purging script and then start rating Rama SIR needs to update for update integration

## CIO Dashboard Meet
Date | Discussion | Meet link: | https://meet.google.com/rsi-hkhh-qvi?authuser=0
2022-07-14
1.Discussed the resolution of tickets with in SLA(6 hours)
2.Provisioning related issues:
## Rama sir had sent a mail saying that He will be
responsible for the provision related issues and will be resolved
by 25th July.
##CmT related issues are marked as closed.
#IP related issue is going to be deployed.
2022-07-22

## Daily Standup call with TCS
Date | Meet link | MOM | Time
2022-06-22 | https://meet.google.com/hdh-urhm-jyw | 1.Inform about Operational Ad requirement 2.Ask BRM team to close the tickets ASAP 3.Pleae attend the meeting with all updates. | 4:30 to 5:30

## AD
DATE | TIME | MEETING LINK | NAME | MOM | action pending | next date
( WHO IS ATTENDED )
2022-01-09 | 10:00AM-11:00AM | https://meet.google.com/kej-vzxv-ucc | Rama sir, Pavan, Umar, Rekha. | MOM of AD Meet dated 05/01/2022 1."DVBoIP Phase V New Service Provider to be created and tag all Hierarchy of DVB IP under this new SP" #Rohan to test and confirm before moving to production. 2."DVBoIP Phase V Daily Burn Rate #Rohan to discuss with business stake holders, review the process note and confirm. 3."Serial number wise tracking of CPE issued to field in ISP(Device validation in ISP)" #Awaiting UAT confirmation 4.NDS Bit set for QR code # Commands required and clarity on requirement is pending from Hathway. 4.Service reactivation DVB IP Live TV- To refund charges for the period of expiry in suspension or to extend validity of active plans for period of suspension # Rohan to test and confirm before moving to production 5.DVBIP Reactivation on the basis of suspend reason # Rohan to test and confirm before moving to production 6.Requirement for Setting the Personal Bit on JIO Verimatrix/NDS Boxes to show the Operator LOGO on TV screen as per the LCO hierarchy #BRM Team to share the API details to OAP. Design document is yet to be shared by all the teams. BRM team already shared the details
2022-01-10 | 3:00PM to 3:30PM | https://meet.google.com/kej-vzxv-ucc | Rama sir,Prem,Krishna,Rekha. | MOM of UPGRADE status call(10-01-2022): #1.load test has to be done and waiting for system to give access to prem 156 server to start the load test. #2.Prem needs to give the billing logs. #3.Need to provide the list of tables by Tomorrow evening. #4.Upload of Source code to git.
2022-01-10 | 10:00AM-10:30AM | https://meet.google.com/kej-vzxv-ucc | Rama sir, Pavan, Umar, Rekha. | MOM OF AD STATUS CALL(10-01-2022): #JVM Upgrade -DVB5 segmentId changes required for DVB5. Rohan confirmed as we need to make this provision from BRM also. Input parameter should be from BRM in FLIST. They are going to send the mail to BRM team regrding this. | We need to call Rohan and confirm | 2022-01-12
2022-01-12 | 10:00Am to 10:45 AM | https://meet.google.com/kej-vzxv-ucc | Rama sir, Pavan, Umar, Rekha. | MOM of AD status call dated (12-02-2022): #New Service Provider to be created and tag all Hierarchy of DVB IP under this new SP "DVBoIP Phase V" #Daily Burn Rate #Service reactivation DVB IP Live TV- To refund charges for the period of expiry in suspension or to extend validity of active plans for period of suspension ---Rohan need to test and confirm. --Rama sir suggested to move Ad items one by one. #JVM Upgrade -DVB5 ---DvB 5 segment id and addition requirement send by Rohan |  | 2022-01-17
2022-01-12 | 3:00PM to 4:00 PM | https://meet.google.com/kej-vzxv-ucc | Prem | MOM of UPGRADE status call(12-01-2022): 1.Need to perform LOAD test BILLING & CANCELATION (Tomorrow from 12PM) 2.Reinstall BRM on 172.20.20.156
2022-03-07 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Rama sir,Pavan,Umar,Dharmendra Nayak. | MOM of TCS UPGRADE call dated (07-03-2022): 1.need to take conformation for deployment time and date AD names: .JVM Bit set .DVBIP Reactivation on the basis of suspend reason - BRM .NAGRA - HD :: Segment configuration - BRM .Retrack JVM command restricted for next 15 minutes - BRM 2.discuss about CPE tracker development from BRM side for validation
2022-03-14 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Umar,Satwik,A.balaji | MOM of TCS AD status call dated (14-03-2022) # discussed on AD deployment for NSTV and JVM set bit. sheduled to 15-03-2022 at 11:30 PM
2022-03-16 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Umar,Dharmendra Nayak,Satwik,A.balaji | MOM of TCS AD status call dated (16-03-2022) # we have deployment today after prafull call need to take conformation from selvan for deployment time and date AD names: 1.JVM set bit 2.NSTV # need to conformation from rama sir for BRD document for faulty module.
2022-03-28 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Umar,Dharmendra Nayak,Satwik | MOM of TCS AD status call dated (28-03-2022) # need to test NSTV retrack action
2022-03-30 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Rama sir,Pavan,Umar,Dharmendra Nayak,Satwik | MOM of TCS AD status call dated (30-03-2022) #need to check bulk location update regarding CPS tracking update. # need to update 3 commands for NSTV sprint 3,retrack was completed for sprint 2. 3 commands are: 1.FINGER PRINT 2.OSD 3.BMAIL
2022-04-06 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Umar,Dharmendra Nayak, Satwik | MOM of TCS AD status call dated (06-04-2022) #development was started for the case when provision orders failed also the ISP transactions need to process and selvan is asking efforts for AD item
2022-04-11 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Umar,Dharmendra Nayak, Satwik | MOM of TCS AD status call dated (11-04-2022) #development was started for the case when provision orders failed also the ISP transactions need to process and selvan is asking efforts for AD item
2022-04-13 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak, Satwik | MOM of TCS AD status call dated (13-04-2022) #AD Items 1. ISP transaction will process when provision orders failed case also . for this, development was started need to do efforts. 2. JVM -reset pin. need to start development and took conformation for efforts and requirement from rama sir.
2022-04-18 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Umar,Dharmendra Nayak | MOM of TCS AD status call dated (18-04-2022) #AD Items 1. ISP transaction will process when provision orders failed.need to send efforts. 2. JVM -reset pin.need to send efforts. 3. upgrade billing and rating.need to perform billing and rating in upgrade server.
2022-04-20 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,Umar,Satwik | MOM of TCS AD status call dated (20-04-2022) #We need to take some process refinement steps for improving turn around time. We will generate VirtualUA at the the time of Inventory upload. And will store in inventory table. If VirualUA is already generated and exist in inventory table then we will update CAS_SUB_ID at the time of service creation and will send same in Activation FLIST request. If VirtualUA exist in Activation Flist then we will send all subsequent MML command except VirtualUA . If VirtualUA is not exist in activation flist then we will send VirtualUA command. # we need to do development for above NAGRA requirement. #JVM Reset Pin - offer to UAT. # ISP tranacations will process when provision order fail,need offer UAT.
2022-04-25 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,Satwik | MOM of TCS AD status call dated (25-04-2022) #need to send test results for ISP transactions and JVM reset pin. #need to develop NAGRA1 and NAGRA2 cas_subscriber_id.
2022-04-27 | 10:00AM to 10:45 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,Umar. | MOM of TCS AD status call dated (27-04-2022) #ISP failure transactions need to send test results. #JVM reset pin need to offer UAT. #NAGRA additional command for Hathway & DSN boxes development was started. #NAGRA enhancement on processing time for CATV,DEN and DSN development was started.
2022-05-02 | 10:00AM to 10:45 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,Umar,satwick | MOM of TCS AD status call dated (02-05-2022) #ISP failure transactions test results are shared. #JVM reset pin offerd to UAT #NAGRA additional command for Hathway & DSN boxes development was done need to test. #NAGRA enhancement on processing time for CATV,DEN and DSN development was done need to test.
2022-05-04 | 10:00AM to 10:45 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,Umar,satwick | MOM of TCS AD status call dated (04-05-2022) #NAGRA additional command for Hathway & DSN boxes development was done need to do test. #NAGRA enhancement on processing time for CATV,DEN and DSN development was done need to test.
2022-05-09 | 10:00AM to 10:45 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,Umar,satwick | MOM of TCS AD status call dated (09-05-2022) #NAGRA additional command for Hathway & DSN boxes development was done.Here changes are apply for hathway only not for DSN. #NAGRA enhancement on processing time for CATV,DEN and DSN development was done need to test. #ISP failed orders deployment was done by 06-05-2022.
2022-05-11 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Dharmendra Nayak,Umar | MOM of TCS AD status call dated (11-05-2022) #NAGRA additional command for Hathway & DSN boxes development was done.Here changes are apply for hathway only not for DSN.development & testing also done #NAGRA enhancement on processing time for CATV,DEN and DSN development was done need to test.
2022-05-23 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Dharmendra Nayak,Umar | MOM of TCS AD status call dated (23-05-2022) #for Isp failed order, need to share artifacts. # need upadte from rama sir about termination dropdown.
2022-05-25 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,Umar,satwick | MOM of TCS AD status call dated (25-05-2022) #shared solution document and checklist for ISP failed orders and NAGRA REQUIREMENTS
2022-06-06 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,Umar,satwick | MOM of TCS AD status call dated (06-06-2022) #pradeep reddy send one mail to our team regarding DB restoration,BRM DB & application upgrade activities,sanity testing for check from our side and also for more tickets coming after upgrade issues.
2022-06-08 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,Umar,satwick | MOM of status call for provision issues dated (08-06-2022) #Discussed about the issues related to Provision orders failed cases. > alternate ID already exist with subscriber ID. #Related to IP, Umar need to confirm from Rama sir to fix the code. #related to Catv, Bouquet id mapping and CAS subscriber id missing in provision orders. #Informed to mam who will provide the tickets related to bouquet mapping.
2022-06-15 | 10:00AM to 10:40 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,Umar,satwick | MOM of status call for provision issues dated (15-06-2022) #some new changes required for nagra additional command for cas_subscriber_id, so need to take conformation from rohan.alraedy discussed with ASAP team. awaiting for UAT #need to revise the efforts for JVM_RESET_PIN. #disussed regarding importance of impacts documentation for ADs.
2022-06-20 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,Umar,satwick | MOM of status call for provision issues dated (20-06-2022) #NAGRA Additional command-21 for Hathway & DSN Boxes, need to test today by sandeep varma. #Sending different broadcast mode for Nagra (HW,DSN &DEN), from BRM side some chages are required, so need to take BRD from TCS Team. #today we have a meet sheduled at 11:00 AM to 11:30 AM for Casting Feature Enabler : QR Code : URL
2022-06-22 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Umar,satwick | MOM of status call for provision issues dated (22-06-2022) #NAGRA development was done from our end and pending from uat. #need to develop new AD regarding FTA block in selective region for DEN ,Hathway and DSN.
2022-06-27 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,satwick | MOM of status call for provision issues dated (27-06-2022) #need to share efforts for AD regarding FTA block in selective region for DEN ,Hathway and DSN. #need to share artifacts for JVM_RESET_PIN. #pending ADs deployment will sheduled on 05-07-2022.
2022-06-29 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,Umar,satwick | MOM of status call for provision issues dated (29-06-2022) #NAGRA Development was completed, need to test orders with ASAP Team today. #BRD approval for FTA block in selective region for DEN ,Hathway and DSN, pending from user side. #need to discuss about AD regarding Casting Feature Enabler : QR Code : URL with rohan.
2022-07-04 | 11:00AM to 11:30 AM | https://meet.google.com/dkp-dhtv-yox | Pavan,Umar,satwick | MOM of status call for provision issues dated (29-06-2022) #.JVM_RESET PIN and FTA BLOCK SELECT REGION FOR DEN (both offered to UAT on 1st july). #.JVM_RESET PIN,FTA BLOCK SELECT REGION FOR DEN,NAGRA Additional command-21 for Hathway Boxes,NAGRA Additional enhancement in processing time(VU ID generation before activation) in CATV,DEN and DSN.(This 4 AD items need to deploy in production by tomarrow).
2022-07-06 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,Umar,satwick | MOM of status call for provision issues dated (06-07-2022) #FTA BLOCK in selective region for DEN testing was plan today, need support from ASAP team. #casting feture enabler need to gather requirement from hatrhway. #in 16. server infranet was not working need to check that.
2022-07-11 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,satwick | MOM of status call for provision issues dated (11-07-2022) #need to take review from rama sir regarding ISP issues AD BRM. #add option for JVM reset PIN from OAP side.already xml file for JVM reset pin was shared to OAP team. #need to send efforts for broadband casting feature from BRM side. #need to gather requirement for FTA from Hathway team.
2022-07-13 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Pavan,Dharmendra Nayak,Umar,satwick | MOM of status call for provision issues dated (13-07-2022) #FTA BLOCKING AD deployment was sheduled on 20th july 2022 from BRM side. remaining ADs need to conform from hathway . #need to take conformation from users regarding operational ADs about multiple task design. #need to send efforts for broadband casting feture from BRM side.
2022-07-18 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Dharmendra Nayak,satwick | MOM of status call for provision issues dated (18-07-2022) #FTA BLOCKING AD deployment was sheduled on 20th july 2022 from BRM side. #need to give support to complete UAT testing by sandeep. #need to share release notes.
2022-07-20 | 10:00AM to 10:30 AM | https://meet.google.com/kej-vzxv-ucc | Dharmendra Nayak,satwick,umar. | MOM of status call for provision issues dated (20-07-2022) #CPE tracking deployment may be sheduled on augest 1st week #JVM reset pin deployment will be sheduled based on customer conformation. #need to monitor the logs related to nagra AD deployment completed by today. #FTA BLOCKING AD was offerd to uat #need to gather requirement for casting feature enabler.